## Instructions & Lists
TZL CEI 2026–2027 PERFORMANCE SCORECARD ¦ USER GUIDE
Purpose | This workbook is the official working scorecard for monthly updates, quarterly reviews, and year-end assessment across TZL CEI, ELMP, Caring & Sharing, and TZL Empower. | Status | Meaning | Categories | Status Override
1. Add or edit initiatives | Use the Initiative Register. Rows are prebuilt through row 104. Enter a new ID, category, target, pace method, owner, and evidence source in the next blank row. | Green | On track / target or expected pace is being met. | TZL CEI
2. Update monthly | On Monthly Scorecard, enter the cumulative/current actual for each initiative in the appropriate month column. Example: if 45 families have been supported by November, enter 45 in November. | Yellow | Needs attention / behind expected pace but recoverable. | ELMP | Green
3. Review status | The workbook compares actual progress with expected progress. Green = on track; Yellow = needs attention; Red = off track; Gray = not updated. | Red | Off track / overdue or materially behind expected pace. | Caring & Sharing | Yellow
4. Override when needed | For event-based or qualitative initiatives, use the Status Override column to select Green, Yellow, or Red. The override becomes the official status. | Not Updated | No current actual has been entered yet. | TZL Empower | Red
5. Quarterly review | Quarterly Review automatically captures the latest actual and calculated status at the end of Oct, Jan, Apr, and Jul.
6. Year-end closeout | Use Year-End Summary to document results, lessons learned, and the next-year decision for each initiative.
7. Action management | Use Action Log for corrective actions, risks, follow-up tasks, and improvement opportunities. |  |  | Pace Methods | Year-End Decision
Program month numbering | 1=Aug, 2=Sep, 3=Oct, 4=Nov, 5=Dec, 6=Jan, 7=Feb, 8=Mar, 9=Apr, 10=May, 11=Jun, 12=Jul. |  |  | Even Pace
Automatic status rule | For measurable initiatives: Green = at least 90% of expected pace; Yellow = 75%–89%; Red = below 75%. Milestones remain on-track before their due month and are evaluated when due. |  |  | Quarterly | Continue
|  |  |  | Milestone | Modify
|  |  |  | Manual | Expand
Retire
Program Month
1
2
3
4
5
6
7
8
9
10
11
12

## Dashboard
TZL COMMUNITY & EDUCATION INITIATIVE ¦ OFFICIAL PERFORMANCE SCORECARD
2026–2027 Program Year ¦ Monthly • Quarterly • Year-End Accountability
Program Year | 2026–2027
Program Month # | 1
As of Date | 2026-08-11
TOTAL INITIATIVES |  | GREEN |  | YELLOW |  | RED |  | NOT UPDATED
47 |  | 0 |  | 0 |  | 0 |  | 100
STATUS BY PROGRAM CATEGORY
Category | Initiatives | Green | Yellow | Red | On Track %
TZL CEI | 12 | 0 | 0 | 0 | 0%
ELMP | 11 | 0 | 0 | 0 | 0%
Caring & Sharing | 11 | 0 | 0 | 0 | 0%
TZL Empower | 13 | 0 | 0 | 0 | 0%
STATUS STANDARD
GREEN | On track | At least 90% of expected pace or milestone met. | YELLOW | Needs attention | 75%–89% of expected pace. | RED | Off track | Below 75% of expected pace or overdue. | GRAY
Not updated
Override | Use Status Override when timing or qualitative judgment makes the automatic pace calculation inappropriate.
Update cycle | Monthly actuals → quarterly scorecard review → year-end closeout and next-year decision.

## Initiative Register
TZL CEI 2026–2027 ¦ MASTER INITIATIVE REGISTER
Add new initiatives in the next blank row. The Monthly, Quarterly, Year-End, and Dashboard sheets are prewired through 100 initiative rows.
Initiative ID | Category | Strategic Priority | Initiative | Metric / Definition | Annual Target | Unit | Pace Method | Start Mo. | Due Mo. | Primary Owner | Required Evidence / Review
CEI-01 | TZL CEI | Grow Partnerships | Active CEI Partnerships | Number of active partnerships across CEI | 12 | partners | Even Pace | 1 | 12 | CEI Board / President | Partner list, confirmations, agreements
CEI-02 | TZL CEI | Grow Partnerships | Partnership Coverage by Pillar | Minimum partners supporting each CEI pillar | 2 | partners per pillar | Manual | 1 | 12 | CEI Board / Program Leads | Partner matrix by pillar
CEI-03 | TZL CEI | Grow Partnerships | Cash Support / Sponsorships | Combined donations, grants, and sponsorships | 30000 | $ | Even Pace | 1 | 12 | CEI Board / Program Leads | Donation ledger, grant awards, sponsorship records
CEI-04 | TZL CEI | Improve Literacy | D9 Literacy Initiatives | Active literacy initiatives operating during the year | 6 | initiatives | Even Pace | 1 | 12 | D9 Literacy Lead | Initiative list, activity records
CEI-05 | TZL CEI | Improve Literacy | D9 Literacy Touchpoints | Monthly literacy activities / touchpoints | 12 | touchpoints | Even Pace | 1 | 12 | D9 Literacy Lead | Attendance, reading prompts, activity logs
CEI-06 | TZL CEI | Improve Literacy | Partner-Hosted Literacy Activities | Literacy activities hosted with partners | 3 | activities | Even Pace | 1 | 12 | D9 Literacy Lead | Partner confirmations, attendance
CEI-07 | TZL CEI | Improve Literacy | Year-End Literacy Impact Summary | Completed annual literacy impact summary | 1 | report | Milestone | 1 | 12 | D9 Literacy Lead | Year-end literacy impact report
CEI-08 | TZL CEI | Board Accountability | Monthly Program Updates | Program updates submitted to the Board | 12 | updates | Even Pace | 1 | 12 | Program Leads | Monthly program updates
CEI-09 | TZL CEI | Board Accountability | Quarterly Scorecard Reviews | Formal scorecard reviews completed | 4 | reviews | Quarterly | 1 | 12 | CEI Board | Board minutes, scorecard review record
CEI-10 | TZL CEI | Board Accountability | Midyear Strategic Update | Midyear strategic review completed | 1 | update | Milestone | 1 | 6 | CEI Board | Midyear report / Board minutes
CEI-11 | TZL CEI | Board Accountability | Year-End Impact Report | Annual CEI impact report completed | 1 | report | Milestone | 1 | 12 | CEI Board | Year-end impact report
CEI-12 | TZL CEI | Board Accountability | Corrective Action for At-Risk Goals | Percent of at-risk goals with documented corrective action | 100 | % | Manual | 1 | 12 | CEI Board / Program Leads | Corrective-action notes, Board minutes
ELMP-01 | ELMP | Build Leaders | Esquires Enrolled | Total Esquires enrolled for the program year | 40 | Esquires | Milestone | 1 | 3 | ELMP Program Staff | Enrollment roster
ELMP-02 | ELMP | Build Leaders | Active Esquires Through May | Esquires remaining active through May | 36 | Esquires | Milestone | 3 | 10 | ELMP Program Staff | Attendance / active roster
ELMP-03 | ELMP | Build Leaders | Primary Success Seminars | Primary Success Seminars completed | 8 | seminars | Even Pace | 3 | 10 | ELMP Program Staff | Agendas, sign-ins, presenter records
ELMP-04 | ELMP | Build Leaders | Life Plan + Evidence Completion | Percent completing Life Plan plus four verified evidence entries | 75 | % | Even Pace | 3 | 10 | ELMP Program Staff | Portfolios, Life Plans, verification records
ELMP-05 | ELMP | Build Leaders | College / Career Exposure | Percent completing at least one college or career exposure activity | 80 | % | Even Pace | 4 | 10 | ELMP Program Staff | Exposure attendance, reflections
ELMP-06 | ELMP | Build Leaders | Achievement Badge Completion | Percent earning at least one approved achievement badge | 60 | % | Even Pace | 3 | 10 | ELMP Program Staff | Badge / progress records
ELMP-07 | ELMP | Build Leaders | Year-End Progress Reviews | Percent receiving a year-end progress review | 100 | % | Milestone | 3 | 10 | ELMP Program Staff | Completed progress reviews
ELMP-08 | ELMP | Build Leaders | Cross-Pillar Leadership Experience | Percent completing one Caring & Sharing and one Empower experience | 75 | % | Even Pace | 4 | 10 | ELMP Program Staff | Service and civic participation records
ELMP-09 | ELMP | Build Leaders | Youth Town Hall Participation | Esquires attending the April Youth Town Hall | 25 | Esquires | Milestone | 9 | 9 | ELMP / Empower Leads | Town Hall sign-in
ELMP-10 | ELMP | Build Leaders | Decision Briefs / Civic Actions | Completed community decision briefs or documented civic actions | 20 | completed | Milestone | 9 | 9 | ELMP / Empower Leads | Decision briefs / action records
ELMP-11 | ELMP | Build Leaders | Tutoring Request Response | Percent of approved tutoring requests acknowledged within 5 business days | 100 | % | Manual | 3 | 10 | ELMP Program Staff | Tutoring request and referral log
CS-01 | Caring & Sharing | Strengthen Families | Family Support Contacts | Documented family-support contacts | 150 | contacts | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | Referral and service log
CS-02 | Caring & Sharing | Strengthen Families | Food Baskets / Equivalent Packages | Food baskets or equivalent packages distributed | 150 | packages | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | Distribution log, household count
CS-03 | Caring & Sharing | Strengthen Families | Family Essentials Kits | Family Essentials Kits distributed | 50 | kits | Milestone | 4 | 4 | Caring & Sharing Co-Directors | Kit count, distribution record
CS-04 | Caring & Sharing | Strengthen Families | Senior Connection / Brother's Keeper | Percent of Senior Connection roster receiving at least two meaningful contacts during the program year | 100 | % | Even Pace | 2 | 12 | Caring & Sharing Co-Directors | Updated contact roster, contact dates, follow-up log
CS-05 | Caring & Sharing | Strengthen Families | Christmas Family Sponsorship | Families sponsored for Christmas support | 2 | families | Milestone | 5 | 5 | Caring & Sharing Co-Directors | Sponsor confirmations, delivery record
CS-06 | Caring & Sharing | Strengthen Families | Organized Service Projects | Organized community service projects completed | 2 | projects | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | Project logs, volunteer records
CS-07 | Caring & Sharing | Strengthen Families | Food Sorted | Food sorted through partner service projects | 1000 | pounds | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | Partner service report
CS-08 | Caring & Sharing | Strengthen Families | CPR / AED Pilot | Youth or adults completing approved CPR/AED pilot | 20 | participants | Milestone | 1 | 12 | Caring & Sharing Co-Directors | Training roster / certificates when applicable
CS-09 | Caring & Sharing | Strengthen Families | Program Resources Raised | Funds raised for Caring & Sharing service | 10000 | $ | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | Donation ledger, fundraising reports
CS-10 | Caring & Sharing | Strengthen Families | Active Caring & Sharing Partners | Active program partners | 5 | partners | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | Partner list / confirmations
CS-11 | Caring & Sharing | Strengthen Families | Referral Review Timeliness | Percent of complete referrals reviewed within 7 business days | 100 | % | Manual | 1 | 12 | Caring & Sharing Co-Directors | Referral log and review dates
EMP-01 | TZL Empower | Empower Communities | Civic Education Symposium Attendance | Total Symposium attendees | 100 | attendees | Milestone | 2 | 2 | TZL Empower Lead | Sign-in / attendance record
EMP-02 | TZL Empower | Empower Communities | Verified Civic Resource Recipients | Symposium participants receiving verified civic resources | 75 | recipients | Milestone | 2 | 2 | TZL Empower Lead | Resource distribution record
EMP-03 | TZL Empower | Empower Communities | Symposium Evaluations | Completed Symposium evaluations | 60 | evaluations | Milestone | 2 | 2 | TZL Empower Lead | Evaluation forms / summary
EMP-04 | TZL Empower | Empower Communities | Increased Civic Understanding | Percent of evaluations reporting increased understanding | 80 | % | Milestone | 2 | 2 | TZL Empower Lead | Evaluation summary
EMP-05 | TZL Empower | Empower Communities | Prospective Volunteers | Prospective volunteers identified through the Symposium | 10 | volunteers | Milestone | 2 | 2 | TZL Empower Lead | Volunteer interest list
EMP-06 | TZL Empower | Empower Communities | Youth Town Hall Attendance | Total Youth Town Hall attendees | 100 | attendees | Milestone | 9 | 9 | TZL Empower Lead | Town Hall sign-in
EMP-07 | TZL Empower | Empower Communities | Esquires at Youth Town Hall | Esquires present at the Youth Town Hall | 25 | Esquires | Milestone | 9 | 9 | TZL Empower / ELMP Leads | Town Hall sign-in
EMP-08 | TZL Empower | Empower Communities | Esquires in Active Roles | Esquires serving in active Town Hall roles | 10 | Esquires | Milestone | 9 | 9 | TZL Empower / ELMP Leads | Role roster
EMP-09 | TZL Empower | Empower Communities | Decision Briefs / Civic Actions | Completed decision briefs or documented civic actions | 20 | completed | Milestone | 9 | 9 | TZL Empower / ELMP Leads | Briefs / action records
EMP-10 | TZL Empower | Empower Communities | Trained Volunteers | Trained Empower volunteers | 15 | volunteers | Even Pace | 1 | 9 | TZL Empower Lead | Training roster
EMP-11 | TZL Empower | Empower Communities | Active Civic Partners | Active civic partners | 3 | partners | Even Pace | 1 | 9 | TZL Empower Lead | Partner list / confirmations
EMP-12 | TZL Empower | Empower Communities | Nonpartisan Review Compliance | Percent of public materials reviewed for nonpartisan compliance before release | 100 | % | Manual | 1 | 12 | TZL Empower Lead | Review checklist / approved materials
EMP-13 | TZL Empower | Empower Communities | After-Action Report Timeliness | Percent of major activities with after-action report completed within 14 days | 100 | % | Manual | 2 | 12 | TZL Empower Lead | After-action reports

## Monthly Scorecard
TZL CEI 2026–2027 ¦ MONTHLY PERFORMANCE SCORECARD
Enter cumulative/current actuals in the month columns. Status updates automatically; use Status Override only when professional judgment is required.
Initiative ID | Category | Strategic Priority | Initiative | Metric | Annual Target | Unit | Pace Method | Start Mo. | Due Mo. | Owner | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Current Actual | Expected to Date | % Annual Target | Pace % | Auto Status | Status Override | Official Status | Last Update | Next Action | Evidence / Link | Notes
CEI-01 | TZL CEI | Grow Partnerships | Active CEI Partnerships | Number of active partnerships across CEI | 12 | partners | Even Pace | 1 | 12 | CEI Board / President | [13 empty] | 1 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CEI-02 | TZL CEI | Grow Partnerships | Partnership Coverage by Pillar | Minimum partners supporting each CEI pillar | 2 | partners per pillar | Manual | 1 | 12 | CEI Board / Program Leads | [14 empty] | #VALUE! |  | Not Updated |  | Not Updated
CEI-03 | TZL CEI | Grow Partnerships | Cash Support / Sponsorships | Combined donations, grants, and sponsorships | 30000 | $ | Even Pace | 1 | 12 | CEI Board / Program Leads | [13 empty] | 2500 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CEI-04 | TZL CEI | Improve Literacy | D9 Literacy Initiatives | Active literacy initiatives operating during the year | 6 | initiatives | Even Pace | 1 | 12 | D9 Literacy Lead | [13 empty] | 0.5 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CEI-05 | TZL CEI | Improve Literacy | D9 Literacy Touchpoints | Monthly literacy activities / touchpoints | 12 | touchpoints | Even Pace | 1 | 12 | D9 Literacy Lead | [13 empty] | 1 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CEI-06 | TZL CEI | Improve Literacy | Partner-Hosted Literacy Activities | Literacy activities hosted with partners | 3 | activities | Even Pace | 1 | 12 | D9 Literacy Lead | [13 empty] | 0.25 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CEI-07 | TZL CEI | Improve Literacy | Year-End Literacy Impact Summary | Completed annual literacy impact summary | 1 | report | Milestone | 1 | 12 | D9 Literacy Lead | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
CEI-08 | TZL CEI | Board Accountability | Monthly Program Updates | Program updates submitted to the Board | 12 | updates | Even Pace | 1 | 12 | Program Leads | [13 empty] | 1 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CEI-09 | TZL CEI | Board Accountability | Quarterly Scorecard Reviews | Formal scorecard reviews completed | 4 | reviews | Quarterly | 1 | 12 | CEI Board | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
CEI-10 | TZL CEI | Board Accountability | Midyear Strategic Update | Midyear strategic review completed | 1 | update | Milestone | 1 | 6 | CEI Board | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
CEI-11 | TZL CEI | Board Accountability | Year-End Impact Report | Annual CEI impact report completed | 1 | report | Milestone | 1 | 12 | CEI Board | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
CEI-12 | TZL CEI | Board Accountability | Corrective Action for At-Risk Goals | Percent of at-risk goals with documented corrective action | 100 | % | Manual | 1 | 12 | CEI Board / Program Leads | [14 empty] | #VALUE! |  | Not Updated |  | Not Updated
ELMP-01 | ELMP | Build Leaders | Esquires Enrolled | Total Esquires enrolled for the program year | 40 | Esquires | Milestone | 1 | 3 | ELMP Program Staff | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-02 | ELMP | Build Leaders | Active Esquires Through May | Esquires remaining active through May | 36 | Esquires | Milestone | 3 | 10 | ELMP Program Staff | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-03 | ELMP | Build Leaders | Primary Success Seminars | Primary Success Seminars completed | 8 | seminars | Even Pace | 3 | 10 | ELMP Program Staff | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-04 | ELMP | Build Leaders | Life Plan + Evidence Completion | Percent completing Life Plan plus four verified evidence entries | 75 | % | Even Pace | 3 | 10 | ELMP Program Staff | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-05 | ELMP | Build Leaders | College / Career Exposure | Percent completing at least one college or career exposure activity | 80 | % | Even Pace | 4 | 10 | ELMP Program Staff | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-06 | ELMP | Build Leaders | Achievement Badge Completion | Percent earning at least one approved achievement badge | 60 | % | Even Pace | 3 | 10 | ELMP Program Staff | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-07 | ELMP | Build Leaders | Year-End Progress Reviews | Percent receiving a year-end progress review | 100 | % | Milestone | 3 | 10 | ELMP Program Staff | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-08 | ELMP | Build Leaders | Cross-Pillar Leadership Experience | Percent completing one Caring & Sharing and one Empower experience | 75 | % | Even Pace | 4 | 10 | ELMP Program Staff | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-09 | ELMP | Build Leaders | Youth Town Hall Participation | Esquires attending the April Youth Town Hall | 25 | Esquires | Milestone | 9 | 9 | ELMP / Empower Leads | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-10 | ELMP | Build Leaders | Decision Briefs / Civic Actions | Completed community decision briefs or documented civic actions | 20 | completed | Milestone | 9 | 9 | ELMP / Empower Leads | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
ELMP-11 | ELMP | Build Leaders | Tutoring Request Response | Percent of approved tutoring requests acknowledged within 5 business days | 100 | % | Manual | 3 | 10 | ELMP Program Staff | [14 empty] | #VALUE! |  | Not Updated |  | Not Updated
CS-01 | Caring & Sharing | Strengthen Families | Family Support Contacts | Documented family-support contacts | 150 | contacts | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | [13 empty] | 12.5 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CS-02 | Caring & Sharing | Strengthen Families | Food Baskets / Equivalent Packages | Food baskets or equivalent packages distributed | 150 | packages | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | [13 empty] | 12.5 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CS-03 | Caring & Sharing | Strengthen Families | Family Essentials Kits | Family Essentials Kits distributed | 50 | kits | Milestone | 4 | 4 | Caring & Sharing Co-Directors | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
CS-04 | Caring & Sharing | Strengthen Families | Senior Connection / Brother's Keeper | Percent of Senior Connection roster receiving at least two meaningful contacts during the program year | 100 | % | Even Pace | 2 | 12 | Caring & Sharing Co-Directors | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
CS-05 | Caring & Sharing | Strengthen Families | Christmas Family Sponsorship | Families sponsored for Christmas support | 2 | families | Milestone | 5 | 5 | Caring & Sharing Co-Directors | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
CS-06 | Caring & Sharing | Strengthen Families | Organized Service Projects | Organized community service projects completed | 2 | projects | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | [13 empty] | 0.16667 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CS-07 | Caring & Sharing | Strengthen Families | Food Sorted | Food sorted through partner service projects | 1000 | pounds | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | [13 empty] | 83.3333 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CS-08 | Caring & Sharing | Strengthen Families | CPR / AED Pilot | Youth or adults completing approved CPR/AED pilot | 20 | participants | Milestone | 1 | 12 | Caring & Sharing Co-Directors | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
CS-09 | Caring & Sharing | Strengthen Families | Program Resources Raised | Funds raised for Caring & Sharing service | 10000 | $ | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | [13 empty] | 833.3333 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CS-10 | Caring & Sharing | Strengthen Families | Active Caring & Sharing Partners | Active program partners | 5 | partners | Even Pace | 1 | 12 | Caring & Sharing Co-Directors | [13 empty] | 0.41667 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
CS-11 | Caring & Sharing | Strengthen Families | Referral Review Timeliness | Percent of complete referrals reviewed within 7 business days | 100 | % | Manual | 1 | 12 | Caring & Sharing Co-Directors | [14 empty] | #VALUE! |  | Not Updated |  | Not Updated
EMP-01 | TZL Empower | Empower Communities | Civic Education Symposium Attendance | Total Symposium attendees | 100 | attendees | Milestone | 2 | 2 | TZL Empower Lead | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-02 | TZL Empower | Empower Communities | Verified Civic Resource Recipients | Symposium participants receiving verified civic resources | 75 | recipients | Milestone | 2 | 2 | TZL Empower Lead | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-03 | TZL Empower | Empower Communities | Symposium Evaluations | Completed Symposium evaluations | 60 | evaluations | Milestone | 2 | 2 | TZL Empower Lead | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-04 | TZL Empower | Empower Communities | Increased Civic Understanding | Percent of evaluations reporting increased understanding | 80 | % | Milestone | 2 | 2 | TZL Empower Lead | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-05 | TZL Empower | Empower Communities | Prospective Volunteers | Prospective volunteers identified through the Symposium | 10 | volunteers | Milestone | 2 | 2 | TZL Empower Lead | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-06 | TZL Empower | Empower Communities | Youth Town Hall Attendance | Total Youth Town Hall attendees | 100 | attendees | Milestone | 9 | 9 | TZL Empower Lead | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-07 | TZL Empower | Empower Communities | Esquires at Youth Town Hall | Esquires present at the Youth Town Hall | 25 | Esquires | Milestone | 9 | 9 | TZL Empower / ELMP Leads | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-08 | TZL Empower | Empower Communities | Esquires in Active Roles | Esquires serving in active Town Hall roles | 10 | Esquires | Milestone | 9 | 9 | TZL Empower / ELMP Leads | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-09 | TZL Empower | Empower Communities | Decision Briefs / Civic Actions | Completed decision briefs or documented civic actions | 20 | completed | Milestone | 9 | 9 | TZL Empower / ELMP Leads | [13 empty] | 0 | #VALUE! |  | Not Updated |  | Not Updated
EMP-10 | TZL Empower | Empower Communities | Trained Volunteers | Trained Empower volunteers | 15 | volunteers | Even Pace | 1 | 9 | TZL Empower Lead | [13 empty] | 1.6667 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
EMP-11 | TZL Empower | Empower Communities | Active Civic Partners | Active civic partners | 3 | partners | Even Pace | 1 | 9 | TZL Empower Lead | [13 empty] | 0.33333 | #VALUE! | #VALUE! | Not Updated |  | Not Updated
EMP-12 | TZL Empower | Empower Communities | Nonpartisan Review Compliance | Percent of public materials reviewed for nonpartisan compliance before release | 100 | % | Manual | 1 | 12 | TZL Empower Lead | [14 empty] | #VALUE! |  | Not Updated |  | Not Updated
EMP-13 | TZL Empower | Empower Communities | After-Action Report Timeliness | Percent of major activities with after-action report completed within 14 days | 100 | % | Manual | 2 | 12 | TZL Empower Lead | [14 empty] | #VALUE! |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 |  |  | Not Updated |  | Not Updated

## Quarterly Review
TZL CEI 2026–2027 ¦ QUARTERLY SCORECARD REVIEW
Quarter-end checkpoints: Q1 = October, Q2 = January, Q3 = April, Q4 = July. Status is calculated against expected pace at each checkpoint.
Quarter-end actuals pull from October, January, April, and July. During each quarterly review, the Board selects the official Green / Yellow / Red status after reviewing pace, timing, evidence, and corrective action.
Initiative ID | Category | Initiative | Target | Unit | Q1 Actual | Q1 Status | Q2 Actual | Q2 Status | Q3 Actual | Q3 Status | Q4 Actual | Q4 Status | Owner | Year-End Status
CEI-01 | TZL CEI | Active CEI Partnerships | 12 | partners | 0 |  | 0 |  | 0 |  | 0 |  | CEI Board / President | Not Updated
CEI-02 | TZL CEI | Partnership Coverage by Pillar | 2 | partners per pillar | 0 |  | 0 |  | 0 |  | 0 |  | CEI Board / Program Leads | Not Updated
CEI-03 | TZL CEI | Cash Support / Sponsorships | 30000 | $ | 0 |  | 0 |  | 0 |  | 0 |  | CEI Board / Program Leads | Not Updated
CEI-04 | TZL CEI | D9 Literacy Initiatives | 6 | initiatives | 0 |  | 0 |  | 0 |  | 0 |  | D9 Literacy Lead | Not Updated
CEI-05 | TZL CEI | D9 Literacy Touchpoints | 12 | touchpoints | 0 |  | 0 |  | 0 |  | 0 |  | D9 Literacy Lead | Not Updated
CEI-06 | TZL CEI | Partner-Hosted Literacy Activities | 3 | activities | 0 |  | 0 |  | 0 |  | 0 |  | D9 Literacy Lead | Not Updated
CEI-07 | TZL CEI | Year-End Literacy Impact Summary | 1 | report | 0 |  | 0 |  | 0 |  | 0 |  | D9 Literacy Lead | Not Updated
CEI-08 | TZL CEI | Monthly Program Updates | 12 | updates | 0 |  | 0 |  | 0 |  | 0 |  | Program Leads | Not Updated
CEI-09 | TZL CEI | Quarterly Scorecard Reviews | 4 | reviews | 0 |  | 0 |  | 0 |  | 0 |  | CEI Board | Not Updated
CEI-10 | TZL CEI | Midyear Strategic Update | 1 | update | 0 |  | 0 |  | 0 |  | 0 |  | CEI Board | Not Updated
CEI-11 | TZL CEI | Year-End Impact Report | 1 | report | 0 |  | 0 |  | 0 |  | 0 |  | CEI Board | Not Updated
CEI-12 | TZL CEI | Corrective Action for At-Risk Goals | 100 | % | 0 |  | 0 |  | 0 |  | 0 |  | CEI Board / Program Leads | Not Updated
ELMP-01 | ELMP | Esquires Enrolled | 40 | Esquires | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
ELMP-02 | ELMP | Active Esquires Through May | 36 | Esquires | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
ELMP-03 | ELMP | Primary Success Seminars | 8 | seminars | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
ELMP-04 | ELMP | Life Plan + Evidence Completion | 75 | % | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
ELMP-05 | ELMP | College / Career Exposure | 80 | % | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
ELMP-06 | ELMP | Achievement Badge Completion | 60 | % | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
ELMP-07 | ELMP | Year-End Progress Reviews | 100 | % | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
ELMP-08 | ELMP | Cross-Pillar Leadership Experience | 75 | % | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
ELMP-09 | ELMP | Youth Town Hall Participation | 25 | Esquires | 0 |  | 0 |  | 0 |  | 0 |  | ELMP / Empower Leads | Not Updated
ELMP-10 | ELMP | Decision Briefs / Civic Actions | 20 | completed | 0 |  | 0 |  | 0 |  | 0 |  | ELMP / Empower Leads | Not Updated
ELMP-11 | ELMP | Tutoring Request Response | 100 | % | 0 |  | 0 |  | 0 |  | 0 |  | ELMP Program Staff | Not Updated
CS-01 | Caring & Sharing | Family Support Contacts | 150 | contacts | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-02 | Caring & Sharing | Food Baskets / Equivalent Packages | 150 | packages | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-03 | Caring & Sharing | Family Essentials Kits | 50 | kits | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-04 | Caring & Sharing | Senior Connection / Brother's Keeper | 100 | % | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-05 | Caring & Sharing | Christmas Family Sponsorship | 2 | families | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-06 | Caring & Sharing | Organized Service Projects | 2 | projects | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-07 | Caring & Sharing | Food Sorted | 1000 | pounds | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-08 | Caring & Sharing | CPR / AED Pilot | 20 | participants | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-09 | Caring & Sharing | Program Resources Raised | 10000 | $ | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-10 | Caring & Sharing | Active Caring & Sharing Partners | 5 | partners | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
CS-11 | Caring & Sharing | Referral Review Timeliness | 100 | % | 0 |  | 0 |  | 0 |  | 0 |  | Caring & Sharing Co-Directors | Not Updated
EMP-01 | TZL Empower | Civic Education Symposium Attendance | 100 | attendees | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-02 | TZL Empower | Verified Civic Resource Recipients | 75 | recipients | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-03 | TZL Empower | Symposium Evaluations | 60 | evaluations | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-04 | TZL Empower | Increased Civic Understanding | 80 | % | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-05 | TZL Empower | Prospective Volunteers | 10 | volunteers | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-06 | TZL Empower | Youth Town Hall Attendance | 100 | attendees | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-07 | TZL Empower | Esquires at Youth Town Hall | 25 | Esquires | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower / ELMP Leads | Not Updated
EMP-08 | TZL Empower | Esquires in Active Roles | 10 | Esquires | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower / ELMP Leads | Not Updated
EMP-09 | TZL Empower | Decision Briefs / Civic Actions | 20 | completed | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower / ELMP Leads | Not Updated
EMP-10 | TZL Empower | Trained Volunteers | 15 | volunteers | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-11 | TZL Empower | Active Civic Partners | 3 | partners | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-12 | TZL Empower | Nonpartisan Review Compliance | 100 | % | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
EMP-13 | TZL Empower | After-Action Report Timeliness | 100 | % | 0 |  | 0 |  | 0 |  | 0 |  | TZL Empower Lead | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated
0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | Not Updated

## Year-End Summary
TZL CEI 2026–2027 ¦ YEAR-END PERFORMANCE SUMMARY
Complete the final three columns during year-end closeout to capture lessons and decide what should continue, change, expand, or retire.
Initiative ID | Category | Strategic Priority | Initiative | Target | Unit | Final Actual | % Target | Final Status | Owner | Year-End Result / Impact | Lessons Learned | Next-Year Decision
CEI-01 | TZL CEI | Grow Partnerships | Active CEI Partnerships | 12 | partners |  |  | Not Updated | CEI Board / President
CEI-02 | TZL CEI | Grow Partnerships | Partnership Coverage by Pillar | 2 | partners per pillar |  |  | Not Updated | CEI Board / Program Leads
CEI-03 | TZL CEI | Grow Partnerships | Cash Support / Sponsorships | 30000 | $ |  |  | Not Updated | CEI Board / Program Leads
CEI-04 | TZL CEI | Improve Literacy | D9 Literacy Initiatives | 6 | initiatives |  |  | Not Updated | D9 Literacy Lead
CEI-05 | TZL CEI | Improve Literacy | D9 Literacy Touchpoints | 12 | touchpoints |  |  | Not Updated | D9 Literacy Lead
CEI-06 | TZL CEI | Improve Literacy | Partner-Hosted Literacy Activities | 3 | activities |  |  | Not Updated | D9 Literacy Lead
CEI-07 | TZL CEI | Improve Literacy | Year-End Literacy Impact Summary | 1 | report |  |  | Not Updated | D9 Literacy Lead
CEI-08 | TZL CEI | Board Accountability | Monthly Program Updates | 12 | updates |  |  | Not Updated | Program Leads
CEI-09 | TZL CEI | Board Accountability | Quarterly Scorecard Reviews | 4 | reviews |  |  | Not Updated | CEI Board
CEI-10 | TZL CEI | Board Accountability | Midyear Strategic Update | 1 | update |  |  | Not Updated | CEI Board
CEI-11 | TZL CEI | Board Accountability | Year-End Impact Report | 1 | report |  |  | Not Updated | CEI Board
CEI-12 | TZL CEI | Board Accountability | Corrective Action for At-Risk Goals | 100 | % |  |  | Not Updated | CEI Board / Program Leads
ELMP-01 | ELMP | Build Leaders | Esquires Enrolled | 40 | Esquires |  |  | Not Updated | ELMP Program Staff
ELMP-02 | ELMP | Build Leaders | Active Esquires Through May | 36 | Esquires |  |  | Not Updated | ELMP Program Staff
ELMP-03 | ELMP | Build Leaders | Primary Success Seminars | 8 | seminars |  |  | Not Updated | ELMP Program Staff
ELMP-04 | ELMP | Build Leaders | Life Plan + Evidence Completion | 75 | % |  |  | Not Updated | ELMP Program Staff
ELMP-05 | ELMP | Build Leaders | College / Career Exposure | 80 | % |  |  | Not Updated | ELMP Program Staff
ELMP-06 | ELMP | Build Leaders | Achievement Badge Completion | 60 | % |  |  | Not Updated | ELMP Program Staff
ELMP-07 | ELMP | Build Leaders | Year-End Progress Reviews | 100 | % |  |  | Not Updated | ELMP Program Staff
ELMP-08 | ELMP | Build Leaders | Cross-Pillar Leadership Experience | 75 | % |  |  | Not Updated | ELMP Program Staff
ELMP-09 | ELMP | Build Leaders | Youth Town Hall Participation | 25 | Esquires |  |  | Not Updated | ELMP / Empower Leads
ELMP-10 | ELMP | Build Leaders | Decision Briefs / Civic Actions | 20 | completed |  |  | Not Updated | ELMP / Empower Leads
ELMP-11 | ELMP | Build Leaders | Tutoring Request Response | 100 | % |  |  | Not Updated | ELMP Program Staff
CS-01 | Caring & Sharing | Strengthen Families | Family Support Contacts | 150 | contacts |  |  | Not Updated | Caring & Sharing Co-Directors
CS-02 | Caring & Sharing | Strengthen Families | Food Baskets / Equivalent Packages | 150 | packages |  |  | Not Updated | Caring & Sharing Co-Directors
CS-03 | Caring & Sharing | Strengthen Families | Family Essentials Kits | 50 | kits |  |  | Not Updated | Caring & Sharing Co-Directors
CS-04 | Caring & Sharing | Strengthen Families | Senior Connection / Brother's Keeper | 100 | % |  |  | Not Updated | Caring & Sharing Co-Directors
CS-05 | Caring & Sharing | Strengthen Families | Christmas Family Sponsorship | 2 | families |  |  | Not Updated | Caring & Sharing Co-Directors
CS-06 | Caring & Sharing | Strengthen Families | Organized Service Projects | 2 | projects |  |  | Not Updated | Caring & Sharing Co-Directors
CS-07 | Caring & Sharing | Strengthen Families | Food Sorted | 1000 | pounds |  |  | Not Updated | Caring & Sharing Co-Directors
CS-08 | Caring & Sharing | Strengthen Families | CPR / AED Pilot | 20 | participants |  |  | Not Updated | Caring & Sharing Co-Directors
CS-09 | Caring & Sharing | Strengthen Families | Program Resources Raised | 10000 | $ |  |  | Not Updated | Caring & Sharing Co-Directors
CS-10 | Caring & Sharing | Strengthen Families | Active Caring & Sharing Partners | 5 | partners |  |  | Not Updated | Caring & Sharing Co-Directors
CS-11 | Caring & Sharing | Strengthen Families | Referral Review Timeliness | 100 | % |  |  | Not Updated | Caring & Sharing Co-Directors
EMP-01 | TZL Empower | Empower Communities | Civic Education Symposium Attendance | 100 | attendees |  |  | Not Updated | TZL Empower Lead
EMP-02 | TZL Empower | Empower Communities | Verified Civic Resource Recipients | 75 | recipients |  |  | Not Updated | TZL Empower Lead
EMP-03 | TZL Empower | Empower Communities | Symposium Evaluations | 60 | evaluations |  |  | Not Updated | TZL Empower Lead
EMP-04 | TZL Empower | Empower Communities | Increased Civic Understanding | 80 | % |  |  | Not Updated | TZL Empower Lead
EMP-05 | TZL Empower | Empower Communities | Prospective Volunteers | 10 | volunteers |  |  | Not Updated | TZL Empower Lead
EMP-06 | TZL Empower | Empower Communities | Youth Town Hall Attendance | 100 | attendees |  |  | Not Updated | TZL Empower Lead
EMP-07 | TZL Empower | Empower Communities | Esquires at Youth Town Hall | 25 | Esquires |  |  | Not Updated | TZL Empower / ELMP Leads
EMP-08 | TZL Empower | Empower Communities | Esquires in Active Roles | 10 | Esquires |  |  | Not Updated | TZL Empower / ELMP Leads
EMP-09 | TZL Empower | Empower Communities | Decision Briefs / Civic Actions | 20 | completed |  |  | Not Updated | TZL Empower / ELMP Leads
EMP-10 | TZL Empower | Empower Communities | Trained Volunteers | 15 | volunteers |  |  | Not Updated | TZL Empower Lead
EMP-11 | TZL Empower | Empower Communities | Active Civic Partners | 3 | partners |  |  | Not Updated | TZL Empower Lead
EMP-12 | TZL Empower | Empower Communities | Nonpartisan Review Compliance | 100 | % |  |  | Not Updated | TZL Empower Lead
EMP-13 | TZL Empower | Empower Communities | After-Action Report Timeliness | 100 | % |  |  | Not Updated | TZL Empower Lead
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0
0 | 0 | 0 | 0 | 0 | 0 |  |  | Not Updated | 0

## Action Log
TZL CEI 2026–2027 ¦ ACTION, RISK & FOLLOW-UP LOG
Use this log for corrective action on red/yellow initiatives, risks, decisions, improvement opportunities, and follow-up commitments.
Date Opened | Initiative ID | Category | Issue / Opportunity | Status | Owner | Due Date | Action / Next Step | Resolution / Result | Date Closed